## Planning
Date | Project |  |  | Arcade | [28 empty] | Burndown Chart
[8 empty] | Sprint 1 | [6 empty] | Sprint 2 | [6 empty] | Sprint 3
Nr | Release | Sprint | User Story | Task / Story | Subtask | Conditions of Satisfaction | Estimated Points | 2014-11-17 | 2014-11-18 | 2014-11-19 | 2014-11-20 | 2014-11-21 | 2014-11-22 | 2014-11-23 | 2014-11-24 | 2014-11-25 | 2014-11-26 | 2014-11-27 | 2014-11-28 | 2014-11-29 | 2014-11-30 | 2014-12-01 | 2014-12-02 | 2014-12-03 | 2014-12-04 | 2014-12-05 | 2014-12-06 | 2014-12-07 | State | Owner | Tester | Completed
| In the release you describe what you need to hand show at the end of the week | The sprint is everything that need to be done in order to make the release | A user story descirbes what should be done (After this phase the customer has an overview of what the concept is going to be) | Task describe the main chuncks of work that need to be done | Break down tasks into subtask (Sketches --> board / cards / pawns / etc) | Here you describe what criteria need to be met, in order for the task to be completed to satisfaction (Our board gameboard design must be full color CMYK and A2 format | Points are estimates that show the priority of the tast | [21 empty] | In a daily standup you check which tasks have been completed | The person responsible | The person responsible to see if conditions of satisfaction are met | Date of completion
| Avalilable Points | [5 empty] | 100
1 | Concept
1.1 |  | Game Design Document, Prototypes, functional and assets
1.1.1 |  |  |  | Game Design Document |  |  | 60
[5 empty] | Brainstorm | Clear idea for our game. | 30 | [21 empty] | Done |  |  | 2016-11-14
[5 empty] | Target Group Analysis |  | 4 | [21 empty] | Busy |  |  | 2016-11-15
[5 empty] | Mechanics Analysis |  | 8 | [21 empty] | Busy
[5 empty] | Game Rules | A document with the game rules explained. | 10 | [21 empty] | Busy
[5 empty] | Game Concept Document | A document with the game concept explained | 18 | [21 empty] | Busy |  |  | 2014-11-20
1.1.2 |  |  |  | Moodboard |  |  | 8
[5 empty] | Moodboard Concept | An A3 size paper with pictures and colours to show the style and theme of the game. | 2 | [21 empty] | ToDo
[5 empty] | Moodboard Discussion |  | 2 | [21 empty] | ToDo
1.1.3 |  |  |  | Sketches |  |  | 16
[5 empty] | Concept Art | A document with concept sketches for the characters and the level. | 8
[5 empty] | Character Design Player | A document with the character design | 8
[5 empty] | Character Design NPC's | A document with the enemy design | 8
1.1.4 |  |  |  | Prototypes |  |  | 48
[5 empty] | Playable version(s) | A playable protoype in GxpEngine | 16
16
1.1.9 |  |  |  | Scrum Meeting |  |  | 10 | [6 empty] | 10 | [15 empty] | Team
2 | Design
Prototype
Game Rules
Concept art
Game tets
Test sheet
Paper Prototype
Feedback forms
[5 empty] | Updated (final) version | [23 empty] | Busy | JAN | TLO
Poster
Design
Print
Trailer Design / Script
|  |  |  | Scrum Meeting |  |  | 10 | [13 empty] | 10 | [8 empty] | Team
3 | Production
Final design of the board
Print
Assembly
….
Game Testing
Feedback forms
Poster
print
Pawns
Trailer design
Recording
Montage
Rule Book
|  |  |  | Scrum Meeting |  |  | 10 | [20 empty] | 10 |  | Team
4 | Polsihing, Final Build, and Delivery
Game manual
Design
Implement
Test
Game Testing and Tweaking
Game Board
Trailer
Presentation
|  |  |  | Scrum Meeting |  |  | 10 | [20 empty] | 10 |  | Team

## Burndown (hidden)
Project | Arcade
Sprint 1
Date | Points
2014-11-16 | 100
2014-11-17 | 100 | 100
2014-11-18 | 100
2014-11-19 | 100
2014-11-20 | 82
2014-11-21 | 82
2014-11-22 | 82
2014-11-23 | 82
Sprint 2
Date | Points
2014-11-23 | 200
2014-11-24 | 200
2014-11-25 | 200
2014-11-26 | 200
2014-11-27 | 200
2014-11-28 | 200
2014-11-29 | 200
2014-11-30 | 200
Sprint 3
Date | Points
2014-11-30 | 100
2014-12-01 | 100
2014-12-02 | 100
2014-12-03 | 100
2014-12-04 | 100
2014-12-05 | 100
2014-12-06 | 100
2014-12-07 | 100
Sprint 4
Date | Points
2014-12-07 | 100
2014-12-08 | 100
2014-12-09 | 100
2014-12-10 | 100
2014-12-11 | 100
2014-12-12 | 100
2014-12-13 | 100
2014-12-14 | 100