## Planning
Date | Project |  |  | Arcade | [28 empty] | Burndown Chart
[8 empty] | Sprint 1 | [6 empty] | Sprint 2 | [6 empty] | Sprint 3
Nr | Release | Sprint | User Story | Task / Story | Subtask | Conditions of Satisfaction | Estimated Points | 2014-11-17 | 2014-11-18 | 2014-11-19 | 2014-11-20 | 2014-11-21 | 2014-11-22 | 2014-11-23 | 2014-11-24 | 2014-11-25 | 2014-11-26 | 2014-11-27 | 2014-11-28 | 2014-11-29 | 2014-11-30 | 2014-12-01 | 2014-12-02 | 2014-12-03 | 2014-12-04 | 2014-12-05 | 2014-12-06 | 2014-12-07 | State | Owner | Tester | Completed
| In the release you describe what you need to hand show at the end of the week | The sprint is everything that need to be done in order to make the release | A user story descirbes what should be done (After this phase the customer has an overview of what the concept is going to be) | Task describe the main chuncks of work that need to be done | Break down tasks into subtask (Sketches --> board / cards / pawns / etc) | Here you describe what criteria need to be met, in order for the task to be completed to satisfaction (Our board gameboard design must be full color CMYK and A2 format | Points are estimates that show the priority of the tast | [21 empty] | In a daily standup you check which tasks have been completed | The person responsible | The person responsible to see if conditions of satisfaction are met | Date of completion
| Available Points | [5 empty] | 100 | [26 empty] | Lead Programmer = David
1 | Concept phase | [32 empty] | Lead Art = Sanne
1.1 |  | Game Design Document | [31 empty] | Lead Game Design = Joey
1.1.1 |  |  |  | Documents |  |  | 60 | [26 empty] | Lead Planner = Tim
[5 empty] | Brainstorm | Clear idea for our game. Basic sketches. | 30 | [21 empty] | Done |  |  | 2016-11-14
[5 empty] | Core mechanics | Document containing core mechanics. | 4 | [21 empty] | Busy |  |  | 2016-11-15
[5 empty] | Conceptual level | Sketched out level concept. | 2 | [21 empty] | Busy
[5 empty] | Game sheet | Completed game sheet document. | 4 | [21 empty] | Busy
[5 empty] | Style sheet | A document containing character and level design explaining how. | 8 | [21 empty] | ToDo
[5 empty] | Flowchart | A flowchart explaining the mechanics | 4 | [21 empty] | ToDo
[5 empty] | Technical requirements | A document containing a list of technical requirements. | 2 | [21 empty] | ToDo
1.1.2 |  |  |  | Moodboard |  |  | 8
[5 empty] | Moodboard Concept | An A3 size paper with pictures and colours to show the style and theme of the game. | 2 | [21 empty] | Busy
1.1.3 |  |  |  | Drawing/design |  |  | 16
[5 empty] | Concept Art | A document with concept sketches for the characters and the level. | 8 | [21 empty] | ToDo
[5 empty] | Character Design Player | A document with the character design | 8 | [21 empty] | ToDo
[5 empty] | Character Design NPC's | A document with the enemy design | 8 | [21 empty] | ToDo
[5 empty] | UI Design |  | 4 | [21 empty] | ToDo
1.1.4 |  |  |  | Prototypes |  |  | 48
[5 empty] | Gameplay prototype | A playable protoype in GxpEngine | 16 | [21 empty] | Busy
[5 empty] | Demo controls | A demo showing the controls. | 4 | [21 empty] | ToDo
2 | Design phase
Prototype
|  |  |  | Documents |  |  | 16
[5 empty] | Game Rules | A document containing a detailed list of all the game rules. | 8 | [21 empty] | ToDo
[5 empty] | Style sheet final | A document containing character and level design explaining how. | 4 | [21 empty] | ToDo
[5 empty] | Workflow design | A document showing how your going to work. | 2 | [21 empty] | ToDo
[5 empty] | Asset list | A document containing a list of all the assets | 4 | [21 empty] | ToDo
[5 empty] | Basic level editor |  | 4 | [21 empty] | ToDo
|  |  |  | Prototype |  |  | 16
[5 empty] | Playtest | Playtesting the game. Receive feedback from others. | 2 | [21 empty] | ToDo
[5 empty] | Technical prototype |  | 4 | [21 empty] | ToDo
[5 empty] | Vertical slice |  | 4 | [21 empty] | ToDo
[5 empty] | Mock up level |  | 2 | [21 empty] | ToDo
[5 empty] | HUD design |  | 2 | [21 empty] | ToDo
[5 empty] | Final art mockup |  | 4 | [21 empty] | ToDo
|  |  |  | Scrum Meeting |  |  | 10 | [13 empty] | 10 | [7 empty] | ToDo | Team
3 | Production/polishing phase
Alpha build
Assets
[5 empty] | Backgrounds | [23 empty] | ToDo
[5 empty] | Characters | [23 empty] | ToDo
[5 empty] | Tiles | [23 empty] | ToDo
[5 empty] | Animations | [23 empty] | ToDo
[5 empty] | Sound/music | [23 empty] | ToDo
[5 empty] | Final menu | [23 empty] | ToDo
Prototype
[5 empty] | Alpha build | [23 empty] | ToDo
[5 empty] | Play test | [23 empty] | ToDo
Polishing
[5 empty] | Bug fixes | [23 empty] | ToDo
[5 empty] | Polishing | [23 empty] | ToDo
[5 empty] | Final test on arcade machine | [23 empty] | ToDo
Pitch
[5 empty] | Presentation | A presentation showing how

## Burndown (hidden)
Project | Arcade
Sprint 1
Date | Points
2014-11-16 | 100
2014-11-17 | 100 | 100
2014-11-18 | 100
2014-11-19 | 100
2014-11-20 | 100
2014-11-21 | 100
2014-11-22 | 100
2014-11-23 | 100
Sprint 2
Date | Points
2014-11-23 | 200
2014-11-24 | 200
2014-11-25 | 200
2014-11-26 | 200
2014-11-27 | 200
2014-11-28 | 200
2014-11-29 | 200
2014-11-30 | 200
Sprint 3
Date | Points
2014-11-30 | 100
2014-12-01 | 100
2014-12-02 | 100
2014-12-03 | 100
2014-12-04 | 100
2014-12-05 | 100
2014-12-06 | 100
2014-12-07 | 100
Sprint 4
Date | Points
2014-12-07 | 100
2014-12-08 | 100
2014-12-09 | 100
2014-12-10 | 100
2014-12-11 | 100
2014-12-12 | 100
2014-12-13 | 100
2014-12-14 | 100